## Meeting 4_14_26
Meeting Date | 2026-04-14 | Members in Attendance
|  | Steve Pawlik | Craig Greer
Meeting called to order @ 7:00 PM |  | Jeff Lukasavich | Mary Martin
by Craig Greer |  | Joseph Petrie | James Hutton
|  | Jeff Licht | Nick Dinardo
Rachel Smolinski
(Red = Absent)
New Business:
1) The kayak launch attached to the dock system at Mayor's Park will be moved from the shore side of the dock
to the deep water side of the dock as it was reported too be to shallow to easily launch in it's current location.
2) Kayak rentals at the Mayor's Park location are still being looked into. The city received a grant from the Erie Canal
Heritage Corridor Foundation for this. Currently the NYS Canal Corporation won't issue any permits for this project
as it is concerned that a 3rd party would be responsible for running the rental operation.
3) The docks at Gratwick Park will be replaced. Currently waiting for a bond to be approved to cover the replacement cost.
The replacement docks will be a floating system similar to the docks at the Botanical Gardens. This project should
be completed by this June 2026.
4) The restoration project at three separate locations along the canal is waiting for permits from the DEC and NYS
Canal Corp. There will be a survey conducted possibly later this month where members of the community can
respond with their opinion on this project. There will be an information sharing meeting at some point in the future
where community members can participate.
5) In the newspaper recently there was an article posted by the NYS Canal Corp. referencing 3 abandoned parcels of land
where easements would be needed in order to complete the bike path extension along Sweeney Street. Steve Pawlik
showed the article (attached below) to the Mayor. Neither the Mayor nor Adam Domardzki were aware of this issue
but they are looking into it.
Old Business:
1) Canal cleanup will take place this Saturday April 18th at 9:00 AM with everyone meeting at Mayor's Park.
Everything is all set and a Port-A-Potty will be on site. Hopefully all Waterfront Commission members will be
there as we are co-sponsors of this project.
2) National Grid's replacement of the power lines running through Mayor's Park won't be taking place until
sometime in 2027. The status of the removal and replacement of the current restrooms is still unknown.
3) The completion of the bike path extension along Sweeney St. will resume as soon as the weather allows.
The meeting was adjourned at 7:20 PM.
The Waterfront Commission will have their next meeting on Tuesday, May 12th, 2026 @ 7:00 PM.

## Meeting 3_10_26
Meeting Date | 2026-03-10 | Members in Attendance
|  | Steve Pawlik | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Mary Martin
by Steve Pawlik |  | Joseph Petrie | James Hutton
Jeff Licht
Nick Dinardo
(Red = Absent)
New Business:
1) Steve talked to the Mayor about Canal Cleanup scheduled for Saturday, April 18th. Our group is registered with
the state. The city recreation department has also been notified.
2) Alex from the recreation dept. said that they are waiting for the asphalt plant to reopen so it can complete
the bike bath extension project. In regards to the portion between Webster St. and its connection to the Oliver
and Sweeney St. part of the bike path they are currently working on ideas that might utilize Tremont St. to make
the connection to Oliver St.
3) Currently they are entertaining the hill above the kayak docks for a possible location for signage identifying
Gateway Park.
4) The docks at Gratwick Park are in need of replacement. The floats supporting the docks are damaged and allowing
water to seep in and causing some sections to start sinking. The major issue is the wooden base of the dock system
which is rotting out leaving no place to anchor the floats to the docks. These docks were installed in 2001. A request
for quotes was sent out and only one quote was received for $142,625.33 from Anchor Marine.
5) The fire tower property on Tonawanda Island is completely cleared out and construction equipment is on site.
6) Emily Root and Larry Young are leaving the Waterfront Commission. Rachel Smolinski has been appointed but was
not in attendance to this meeting.
7) Jeff Lukasavich has agreed to take over our webpage as Gabby Richards has left the Waterfront Commission.
Jeff has requested being appointed to the Waterfront Commission as well.
Old Business:
1) The Niagara River Keepers project along the canal is in the process of obtaining all necessary permits from the NYS
Canal Corp. After that approval the DEC & Corp of Engineers will also need to approve this project. Signage will be
be placed along this area in the near future with a QR code that can scanned for information about the project.
Attached to these minutes are files showing the different phases of this proposed project.
The meeting was adjourned at 7:35 PM.
The Waterfront Commission will have their next meeting on Tuesday, April 14th, 2026 @ 7:00 PM.

## Meeting 2_10_26
Meeting Date | 2026-02-10 | Members in Attendance
|  | Steve Pawlik | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Mary Martin
by Steve Pawlik |  | Joseph Petrie | Larry Young
|  | Jeff Licht | James Hutton
Nick Dinardo
(Red = Absent)
New Business:
1) Steve talked to the Mayor about signage that would let boaters approaching from the water know that they were at
Gateway Park. The Mayor said they were considering a mural on the stone retention wall at Gateway Park to
identify the area. We are also looking into signage that would inform people using the bike path where they
maneuver through Gateway Park and connect with the bike path that heads down Sweeney St. and will now
travel all the way to the Botanical Garden Park and boat launch.
2) The Canal Cleanup Day is scheduled for Saturday, April 18th. More details as they become available.
3) Jeff Lukasavich has agreed to take over our webpage where Gabby Richards has left off with approval of the Mayor.
4) Our commission members welcomed new member Nick Dinardo.
3) The city has received $320,000 to fund some shoreline restoration along the canal. The funding will facilitate
parts B & C of a three part restoration plan. There is another proposal to fund part A of the project. The projects work to
remove invasive plant species and replace them with native plants. Several designated fishing spots will also be built.
Signs will be placed in the project areas that will have an informational QR code that people can scan. It is our understanding
that this code will link people to information about this project as well as provide a survey that people can participate in
to give their feedback about the project. Permits have been drafted to get all approvals for this work to be done.
4) The city also received a 5.6 million dollar grant to provide infrastructure support for the new apartment complex that will be
built on Tonawanda Island. This infrastructure will also provide support for future development on Tonawanda Island.
Old Business:
1) Members were asked to review the pictures that community members submitted and pick 10 that they would like to
see on our webpage. Members will bring their picks to our next meeting for review.
The meeting was adjourned at 7:35 PM.
The Waterfront Commission will have their next meeting on Tuesday, March 10th, 2026 @ 7:00 PM.

## Meeting 1_13_26
Meeting Date | 2026-01-13 | Members in Attendance
|  | Steve Pawlik | Craig Greer
Meeting called to order @ 7:00 PM |  | Emily Root | Ben Meyer
by Craig Greer |  | Joseph Petrie | Larry Young
|  | Jeff Licht | James Hutton
|  | Gabby Richards | Mary Martin
Nick Dinardo
(Red = Absent)
New Business:
1) There are no updates on the Buffalo River Keeper's grant that is currently under consideration.
2) The commission reviewed the revenue reports for the marina, Lumberjacks restaurant and Gateway docking fees.
3) Donna Braun is currently maintaining our new webpage and Gabby Richards has been elected to the common council.
It is our understanding that Gabby will no longer be on the Waterfront Commission so we will need to have someone
else work with Donna Braun to maintain our webpage. Emily Root said she will touch base with Gabby to discuss the
the status of our webpage.
3) Attached to these minutes you will find the pictures the community have submitted for possible posting on our webpage.
4) Our commission welcomed newly appointed member Mary Martin.
5) Current member Ben Meyer informed us that he will no longer be able to be a member. We want to thank Ben for his many
years of service.
6) We are waiting to have the Canal Cleanup date announced. We believe it might be either April 18th or the 25th.
Old Business:
1) The bike path extension along Sweeney St. will have the remaining construction resumed in the spring. We have been
informed that this section of Sweeney St. will be paved and mail boxes returned to their original side of the street when
construction is complete.
2) The commission members still want to work on a plan to provide signage directing people through Gateway Park to
connect with the bike paths on either side of the Gateway location. It was also discussed that there is no signage that
would identify the Gateway Park to people approaching from the water.
The meeting was adjourned at 7:45 PM.
The Waterfront Commission will have their next meeting on Tuesday, February 10th, 2026 @ 7:00 PM.

## Sign in Sheet
Waterfront Commission Sign In Sheet
Meeting Date: April 14th, 2026
Name | Email | Phone # | Signature
Joseph Petrie | josephpetrie95@gmail.com | 716-550-3333
Nick Dinardo | nmdinardo7@gmail.com | 716-513-4512
Mary Martin | martinmary1119@gmail.com | 716-954-3628
Jeff Licht | jlicht7048@aol.com | 716-628-0693
Craig Greer | cgreer51@aol.com | 803-243-5713
Steve Pawlik | pawlik1100@verizon.net | 716-432-9877
Rachel Smolinski | RachelESmolinski@gmail.com | 716-534-5877
Jeff Lukasavich | jefflukes@gmail.com | 716-310-0644